## ArtProject
Task_Mode | Name | Duration | Start_Date | Finish_Date | Percent_Complete | Cost | Scheduled_Work | WBS
Manually Scheduled | Art Gathering | 41 days | December 19, 2018 8:00 AM | February 13, 2019 5:00 PM | 1 | 0 | 960h | 1
Auto Scheduled | Sculpture Gathering | 40 days | December 19, 2018 8:00 AM | February 12, 2019 5:00 PM | 1 | 0 | 320h | 1.1
Auto Scheduled | Painting Gathering | 41 days | December 19, 2018 8:00 AM | February 13, 2019 5:00 PM | 1 | 0 | 640h | 1.2
Manually Scheduled | Brochure Setup | 49 days | December 19, 2018 8:00 AM | February 24, 2019 5:00 PM | 0.5 | 0 | 392h | 2
Auto Scheduled | Brochure Design | 29 days | December 19, 2018 8:00 AM | January 28, 2019 5:00 PM | 0.5 | 0 | 232h | 2.1
Auto Scheduled | Brochure Distribution | 20 days | January 29, 2019 8:00 AM | February 24, 2019 5:00 PM | 0.5 | 0 | 160h | 2.2
Auto Scheduled | Team Meeting | 0 days | February 24, 2019 5:00 PM | February 24, 2019 5:00 PM | 0 | 0 | 0h | 2.3
Manually Scheduled | Pre-Setup | 1 day | February 24, 2019 8:00 AM | February 24, 2019 5:00 PM | 0 | 20 | 32h | 3
Auto Scheduled | Rental Space | 1 day | February 24, 2019 8:00 AM | February 24, 2019 5:00 PM | 0 | 5 | 8h | 3.1
Auto Scheduled | Table Setup | 1 day | February 24, 2019 8:00 AM | February 24, 2019 5:00 PM | 0 | 5 | 8h | 3.2
Auto Scheduled | Easel Setup | 1 day | February 24, 2019 8:00 AM | February 24, 2019 5:00 PM | 0 | 5 | 8h | 3.3
Auto Scheduled | Chair Setup | 1 day | February 24, 2019 8:00 AM | February 24, 2019 5:00 PM | 0 | 5 | 8h | 3.4
Auto Scheduled | Team Meeting | 0 days | February 24, 2019 5:00 PM | February 24, 2019 5:00 PM | 0 | 0 | 0h | 3.5
Manually Scheduled | Art Display | 1 day | February 25, 2019 8:00 AM | February 25, 2019 5:00 PM | 0 | 0 | 40h | 4
Auto Scheduled | Hosting | 1 day | February 25, 2019 8:00 AM | February 25, 2019 5:00 PM | 0 | 0 | 40h | 4.1
Auto Scheduled | Team Meeting | 0 days | February 25, 2019 5:00 PM | February 25, 2019 5:00 PM | 0 | 0 | 0h | 4.2
Manually Scheduled | Post-Setup | 1 day | February 26, 2019 8:00 AM | February 26, 2019 5:00 PM | 0 | 0 | 40h | 5
Auto Scheduled | Teardown | 1 day | February 26, 2019 8:00 AM | February 26, 2019 5:00 PM | 0 | 0 | 32h | 5.1
Auto Scheduled | Rental Returns | 1 day | February 26, 2019 8:00 AM | February 26, 2019 5:00 PM | 0 | 0 | 8h | 5.2
Auto Scheduled | Team Meeting | 0 days | February 26, 2019 5:00 PM | February 26, 2019 5:00 PM | 0 | 0 | 0h | 5.3