## Slide 1: Project Reporting
Lesson 10
Microsoft Project 2013

## Slide 2: Objectives

## Slide 3: Software Orientation
The new Report Ribbon makes locating and selecting a report easier than ever before. With predefined dashboard reports, the user can show an overview of the project, project burn- down, cost overview, work overview and many more.

## Slide 4: Software Orientation
The Project Overview Dashboard provides the basic information need to present project performance to date, which tasks are late, which milestones are coming due, and an overall percent complete.

## Slide 5: Activate and Print a Dashboard Report
Using a Dashboard report you can quickly see all of the major information about your project, then print the information.

## Slide 6: Step by Step: Select and Print a Dashboard Report
  GET READY. Before you begin these steps, launch Microsoft Project 2013.
  1. OPEN the Don Funk Music Video 10M project schedule.
  2. SAVE the file as Don Funk Music Video 10.
  3. On the ribbon, click the Project tab. In the Status group click the calendar icon in the Status Date field. Microsoft Project displays the Status Date dialog box.
  4. In the Select Date: field type or select 6/10/16. Your screen should look like the figure at right.

## Slide 7: Step by Step: Select and Print a Dashboard Report
  5. Click OK or press Enter to close the Status Date dialog box. You set the Status Date to tell Microsoft Project you want information as of this date.
  6. On the ribbon, click the Report tab and then select the Dashboards button. From the dropdown menu that appears, select Project Overview. Your screen should look similar to the figure above.

## Slide 8: Step by Step: Select and Print a Dashboard Report
  7. On the ribbon, click the File tab and then select Print from the navigation bar on the left side of the screen. Your screen should look similar to the figure at right. You may notice that some of the report is cut |off at the right side of the print pre- view area.
Notes:     Take Note: You may or may not see the Print Preview screens in color, depending upon the printer and print drivers you have installed.

## Slide 9: Step by Step: Select and Print a Dashboard Report
  8. At the lower right of the Settings section, click the Page Setup hyperlink. Microsoft Project displays the Page Setup dialog box.
  9. On the Page tab, in the Scaling section, click Fit to: and choose 1 against the pages wide by and tall boxes. Your dialog box should look like the figure at right.

## Slide 10: Step by Step: Select and Print a Dashboard Report
  10. Now select the Margins tab. Set all margins to 0.5 inches. Click the OK to close the dialog box. Your screen should now look like the figure below.
  11. SAVE the project schedule.
PAUSE. LEAVE Project open to use in the next exercise.

## Slide 11: Step by Step: Select and Print a Dashboard Report
A report is anything the project manager uses to transmit information about the project. Most all reports are done in writing, using both words and graphics. Some reports are made available through dashboards.
A dashboard is a generic term used to mean an easy-to-read, single-page interface (usually centrally located–such as a SharePoint web page) that senior management can quickly view to obtain a high-level view of current project status.

## Slide 12: Customize and Print a Report
Using the new options of the reports feature in Microsoft Project 2013 allows you to fully customize the information you wish to include in the report.

## Slide 13: Step by Step: Create, Customize and Print a Report
GET READY. USE the project schedule you created in the previous exercise.
  1. Click the Report tab. On the ribbon, click the New Report button.
  2. On the drop- down menu that appears, click Table.
  3. In the Report Name box that appears, name the new report Remaining Work Report and then click OK. Your screen should look like the figure above.

## Slide 14: Step by Step: Create, Customize and Print a Report
  4. At the top of the field list at the right of the screen, click Resources.
  5. Using the scroll box at the right of the field list box, navigate down until the Work fields are visible and then select the expand button next to Work.
  6. Select the check box next to Remaining Work.
  7. In the Filter box, select Resources: Work.
  8. In the Sort by box, select Name.

## Slide 15: Step by Step: Create, Customize and Print a Report
  9. Auto-fit the Name and Remaining Work columns (make them wider so all information fits on one line) and then center the entire table on the screen under the report name.
  10. Click the File tab and then select Print. You will note that the report may not be centered on the page. This is because the previous report was on Landscape orientation.
  11. In the settings section, change the orientation to Portrait.
  12. Click the return arrow at the top.
Notes:     Take Note: At this point, you can print the information by clicking the Print button (the print preview is adequate for purposes of this lesson). When printing in Microsoft Project 2013, there are additional options in the Print dialog box (the Print command is accessed from the File tab). For example, you can print specific date or page ranges.

## Slide 16: Step by Step: Create, Customize and Print a Report
  13. Click the minus sign on the zoom slider at the lower right portion of the screen two or three times. Manually move the table and the report name box to the center of the page. You will note page breaks are indicated by the dashed lines.

## Slide 17: Step by Step: Create, Customize and Print a Report
  14. Click the File tab and then select Print. You will note that the report is now centered on the page.
  15. SAVE the project schedule.
PAUSE. LEAVE Project open to use in the next exercise.
Printing information from a project schedule to share with stakeholders is a common activity for project managers.
Stakeholders are the people or organizations that might be affected by project activities and can range from resources working on the project to customers receiving the project deliverables.

## Slide 18: Reporting Project Status
Microsoft Project provides many different ways to report a project’s status in terms of budget or variance.
A key part of a project manager’s job is knowing which stakeholders need to see which details in which format.

## Slide 19: Step by Step: Report Project Variance with a “Stoplight” View
USE the project schedule you created in the previous exercise.
  1. Click the View tab, then in the Task views group, select Other Views then select More Views. In the list select Task Sheet and then click Apply. Microsoft Project displays the Task Sheet view.
  2. Select the Tables button and then click Cost.
  3. Click on the Project tab, and then click the Custom Fields button. The Custom Fields dialog box appears.
  4. Under the Field label at the top of the dialog box, make sure that Task is selected. In the Type box, select Number from the dropdown list.

## Slide 20: Step by Step: Report Project Variance with a “Stoplight” View
  5. In the Field list, select Overbudget (Number3).
  6. Under the Custom attributes label, click the Formula button. The Formula dialog box is displayed. The formula shown in this dialog box has been pre-entered for accuracy and to save time. Your screen should look similar to the figure below.

## Slide 21: Step by Step: Report Project Variance with a “Stoplight” View
The formula evaluates each task’s cost variance.
If the task is above 20 percent above baseline, the formula assigns the number 30 to the task; if it is between 20 percent and 10 and percent, a 20; and if below 10 percent, a 10. If the task does not fit within those criteria, such as the case with a milestone task which should have no costs, the formula returns a zero value.
Note: For the purposes of this project, a variance of 20 percent above baseline has been decided on by the project manager and sponsor as the maximum tolerance level.

## Slide 22: Step by Step: Report Project Variance with a “Stoplight” View
  7. Click Cancel to close the Formula dialog box.
  In the Custom Fields dialog box, under the Values to display label, click the Graphical Indicators button.
  The Graphical Indicators dialog box appears. This dialog box enables you to specify a unique graphical indicator to display, depending on the value of a field for each task. In this usage, the values returned from the formula in the figure on slide 20 are used to assign the graphical indicator.
  To save time, the indicators have already been selected.

## Slide 23: Step by Step: Report Project Variance with a “Stoplight” View
  9. Click the first cell under the Image column heading, and then click the down arrow. Here you can see the many graphical indicators you can associate with the values of fields.
  10. Click Cancel twice to close the Graphical Indicators dialog box, and then click Cancel again to close the Custom Fields dialog box.
  11. Right-click the Fixed Cost column heading. Select Insert Column from the list.
  12. From the keyboard, start typing the word “Over”.
Notice how Project narrows the list down as you type. You can also navigate using the scroll bar to Overbudget (Number3).

## Slide 24: Step by Step: Report Project Variance with a “Stoplight” View
Microsoft Project displays the Overbudget column in the Cost table. Your screen should look similar to the figure below.

## Slide 25: Step by Step: Report Project Variance with a “Stoplight” View
The custom field Overbudget (Number3) displays a graphical indicator that represents one of three different levels of cost variance.
The graphical indicators will change, according to the ranges specified in the formula, as each task’s cost variance changes. This is a useful format for identifying tasks whose cost variance is higher than you would like (as indicated by the red and yellow indicators).
This makes it easy for any stakeholder to quickly scan the task list and locate tasks that need further attention.
  13. SAVE the project schedule.
PAUSE. LEAVE Project open to use in the next exercise.

## Slide 26: Step by Step: Report Project Variance with a “Stoplight” View
In this exercise, you used a custom field with a custom formula to create a custom stoplight report.
As a project manager, you will find many ways to present the current status of your project. Bear in mind the audience of the report. For example, you will want to present high level information to upper management. Conversely, you will want to give detailed information to the project team.
Notes:     Cross Ref: You will learn more about saving Microsoft Project data in other formats in lesson 12.

## Slide 27: Using Visual Reports Stop on thurs
The Visual Reports feature of Microsoft Project 2013 combines the power of Microsoft Excel and Microsoft Visio with the data of your project to create high-impact, visually centered reports.
You can use a preformatted report, edit a report, or create a new report that includes a specific set of fields from Microsoft Project.

## Slide 28: Step by Step: Create a Visual Report
USE the project schedule you created in the previous exercise.
  1. On the ribbon, click the Report tab, and then select the Visual Reports button. The Visual Reports–Create Report dialog box appears. Your screen should look like the figure at right.
  2. Click the Task Usage tab, and then click Cash Flow Report.

## Slide 29: Step by Step: Create a Visual Report
  3. In the Select level of usage data to include in the report: box, select Months.
  4. Click the View button. The Visual Report engine gathers data from your project file and builds an Online Analytical Processing (OLAP) cube. The application Microsoft Excel opens and the report is presented in Chart form from a preformatted report template. Your screen should look similar to the figure above.

## Slide 30: Step by Step: Create a Visual Report
  5. At the bottom of the Excel window, select the Task Usage sheet tab.
  6. In the PivotTable Field List box, navigate to the Time field. Place your cursor on Monthly Calendar and drag it to the Rows box. Your screen should look similar to the figure at right.

## Slide 31: Step by Step: Create a Visual Report
  7. In the PivotTable area, click the expand button next to the year 2016, to reveal all the available time data. Your screen should look similar to the figure at right.

## Slide 32: Step by Step: Create a Visual Report
  8. Click the Chart1 sheet tab at the bottom of the screen. Your screen should look similar to the figure at right.
  9. Save the Excel visual report as Don Funk Cash Flow in your My Documents folder or another folder directed by your instructor.

## Slide 33: Step by Step: Create a Visual Report
  10. CLOSE Microsoft Excel.
  11. CLOSE the Visual Reports Dialog box.
  12. SAVE the project schedule.
PAUSE. LEAVE Project open to use in the next exercise.
In this exercise, you created a new visual report.
A visual report is a specific type of report that utilizes the combined the power of either Microsoft Excel or Microsoft Visio and the data which you have created in your project file.
The data is translated into pivot tables and graphs. You must have Microsoft Excel 2007 or newer to view the Excel reports with the Visual Reports feature.
You must have Microsoft Visio 2007 Professional or higher installed on your system to view the Visio reports. If this is not installed, the Visio reports will not be listed in the dialog box.

## Slide 34: Customizing and Printing a View
Using a view, you can see your project schedule information on-screen.
You can change what you see by customizing the view.
You can also apply these customized views to print the information on paper.

## Slide 35: Step by Step: Customize and Print a Gantt Chart View
USE the project schedule you created in the previous exercise.
  Click the View tab, then select the Gantt Chart button.
  2. Click the File tab and then click Print. Microsoft Project displays print options on the left side and the Gantt Chart view in the right side, which is the Print Preview window. Your screen should look like the figure above.

## Slide 36: Step by Step: Customize and Print a Gantt Chart View
  3. On the Print Preview toolbar, click the Page Right and/or Page Down button to display different pages.
  4. On the Print Preview toolbar, click the Multiple Pages button. Most of the pages of the Gantt Chart appears in the Print Preview window. When the multiple pages Print Preview is active the printed output is displayed on separate sheets. You navigate using the scroll control at the bottom of the Print Preview pane. The Page Right, Page Left, Page Up, and Page Down buttons are inactive. The paper size displayed is determined by your printer settings. Your screen should look similar to the figure on the next slide.

## Slide 37: Step by Step: Customize and Print a Gantt Chart View

## Slide 38: Step by Step: Customize and Print a Gantt Chart View
The left side of the Print Preview Toolbar status bar should read “3 rows 3 columns.” In the Print Preview window, this means there are three rows of pages by three columns of pages, for a total of nine pages. The status bar can help you quickly determine the total number of pages your printed view will be.
  5. On the Print Preview toolbar, click the One Page button. The first page of the Gantt Chart is displayed.
  6. Click the Page Setup hyperlink. The Page Setup dialog box appears. This is the same dialog box that would appear if you selected the Page Setup option on the File tab.
  7. Click the Header tab. You want to add the company name to the header that prints on each page.

## Slide 39: Step by Step: Customize and Print a Gantt Chart View
  8. There are three Alignment tabs in the center section of the Header tab box. Select Center if it is not already selected. In the General box, click Company Name and then click the Add button next to the General box. Microsoft Project places the following code into the header: &[Company]. The software also displays a preview in the Preview window of the Page Setup dialog box.
  9. Click the Legend tab. You want to change some of the content of the Gantt Chart view’s legend.
  10. There are three Alignment tabs in the center of the Legend tab box. Click the Left tab. Currently, Microsoft Project is formatted to print the project title and current date on the left side of the legend. You also want to print the start date and duration on the right side of the legend.

## Slide 40: Step by Step: Customize and Print a Gantt Chart View
  12. Click the Right Alignment tab. Click the Right Alignment box, press Enter, and then type Start: followed by a space.
  13. In the General box, select Project Start Date from the dropdown list. Click the Add button next to the General box. Microsoft Project adds the label and code for the project start date to the legend.
  14. Press Enter to add a second line to the legend and then type Duration: followed by a space.
  15. In the Project Fields box, select Scheduled Duration from the dropdown list. Click the Add button next to the Project Fields box. Microsoft Project adds the label and code for project duration to the legend.

## Slide 41: Step by Step: Customize and Print a Gantt Chart View
  16. In the Width box, type or use the scroll buttons to enter 3. This increases the width of the box that appears on the left side of the legend. Your screen should look similar to the figure above.

## Slide 42: Step by Step: Customize and Print a Gantt Chart View
  17. Click OK to close the Page Setup dialog box. Microsoft Project applies the custom changes to the legend.
  18. Move your mouse cursor to the lower left corner of the page preview (your cursor appears as a magnifying glass). Click the lower left corner of the page. Microsoft Project zooms in to show the legend. Your screen should look similar to the figure on the next slide.
Notes:     Take Note: At this point, you can print the project schedule by clicking the Print button (the print preview is adequate for purposes of this lesson). When printing in Microsoft Project 2013, there are additional options in the Print dialog box (the Print command is accessed from the File tab). For example, you can print specific date or page ranges.

## Slide 43: Step by Step: Customize and Print a Gantt Chart View

## Slide 44: Step by Step: Customize and Print a Gantt Chart View
  The data you added to the legend will print on every page of the printed output.
  19. Click the Task tab to return to the Gantt Chart view. Take note that although you did not print, your changes to the header and the legend will be saved when you save the project file.
  20. SAVE the project schedule.
PAUSE. If you are continuing to the next lesson, keep Project open. If you are not continuing to additional lessons, CLOSE Project.

## Slide 45: Step by Step: Customize and Print a Gantt Chart View
In a view, you can enter, read, edit, and print information. In a report, you can only print the information, you cannot change the data. Printing a view allows you to provide, on paper, almost everything you see on your screen. You can print any view you see in Microsoft Project, with just a few exceptions.
You cannot print form views (for instance, Task Form) or certain diagrams, such as the Relationship Diagram.
If you have two views displayed in a combination view (one view in the top pane and the other view in the bottom pane), only the view in the active pane will print.
Notes:     Cross Ref: For a review of the types of views, including form views, refer back to Lesson 8.

## Slide 46: Step by Step: Customize and Print a Gantt Chart View
In this lesson, you applied some custom formulas and graphical indicators to make it simple to review the status of tasks using the Task Sheet view.
Communicating the project status to stakeholders is one of the most important functions of a project manager and one that may occupy a significant portion of your working time.
It is imperative that the project manager know who needs to know the project status and why, as well as in what format and level of detail these people need the information.
The time to find the answers to these questions is in the initial planning stages of the project.

## Slide 47: Step by Step: Customize and Print a Gantt Chart View
Once work on the project has commenced, your primary communication task will be reporting project status. This can take several forms:
Status reports describe where the project is in terms of scope, cost, and schedule. These are often referred to as the triple constraints, which is a popular model of project management.
Progress reports that provide the specific accomplishments of the project team.
Forecasts that predict future project performance.

## Slide 48: Step by Step: Customize and Print a Gantt Chart View
Standard report formats may already exist if your organization is highly focused on projects and project management. If your organization does not have standard reports, you may be able to introduce project status formats that are based on clear communication and project management principles. You may be able to report project status using some of the following:
Printing the Project Overview dashboard report.
Copying Microsoft Project data to other applications. For example, you could copy the Calendar view to Microsoft Office Word or Microsoft Office PowerPoint.
Saving Microsoft Project data in other formats, such as Excel, HTML or GIF.

## Slide 49: Step by Step: Customize and Print a Gantt Chart View
It is important to keep in mind that the part of the project schedule you see on your screen is only a small part of the total project. For example, to print a six-month project with 75 tasks may require more than a dozen letter-sized pages.
In general, Gantt Charts and Network Diagrams can use significant amounts of paper on large projects.
Some experienced project managers who regularly use Microsoft Project print their projects on poster-sized paper using plotters (a type of printer that draws pictures or graphs using attached pens) or other specialized printing equipment.

## Slide 50: Step by Step: Customize and Print a Gantt Chart View
Projects with several hundred tasks or long time frames will not print legibly on letter or legal-sized paper.
To reduce the number of required pages, you can print just summary tasks or filtered data.
If you are interested in a specific timeframe, you can print just that portion of the timescale, which is the band across the top of the Gantt Chart grid that denotes units of time.
A filter could be applied to display only the information that is of interest to a specific audience. In any case, it is a good idea to preview the views you want to print.
By using the Page Setup dialog box along with the Print Preview window, you can control many features of the view to be printed. For example, you can set the number of pages on which the view will be printed, apply headers and footers, and determine content that appears in the legend of the Gantt Chart and some other views.
Notes:     Take Note: When printing in views that contain a timescale, such as the Gantt Chart view, you can change the number of pages required by adjusting the timescale before printing. To adjust the timescale so that it shows the largest time span in the smallest number of pages, click the View tab, then in the Zoom group, click Entire Project.

## Slide 51: Skill Summary